## Sheet1
No | Dates are getting tracked, but not effort. No evidence of effort estiamtion or don't see effort tracked via PMWB.
No | Dates are getting tracked, but not effort. No evidence of effort estiamtion or don't see effort tracked via PMWB.
No | I don't know really how efforts are getting tracked. Don't see any DQI tracker maintained or neither its tracked through PMWB
NA | Is any review happened?
NA
No | Unable to locate skill building plan/template
No | Eliayraja details are missing in the PMWB staffing sheet.
No | No evidence of it.
Yes
No | I see multiple tasks have schedule slippage,but don't see any evidence of CAPA for same.
No | No eveidence of consolidated review record maintained and tracked.
NA
NA
NA
NA
No | 1) Don't see DQI tracker 2) Don't see DQI metrics for all engineers, not justification given. 3) Coding productivity goal looks to be wrong, not sure where it comes. Assuming its all C# 90 LOC/day looks very very high.
No | No evidence of SMR for Jun'17.

## Sheet2
NA
NA
NA
NA
NA
NA
NA
NA
NA
NA
NA
NA